## Master Project Schedule
MASTER PROJECT SCHEDULE TEMPLATE
| PROJECT TITLE |  | START DATE
| Sistema de Monitoreo de Salud |  | 2025-02-20 |  |  | PROJECT DURATION
| PROJECT MANAGER |  | END DATE |  |  | in days
| Tenoch Moreno |  | 2025-05-09 |  |  | 79
WBS NO. | TASK NAME | STATUS | ASSIGNED TO | START DATE | END DATE | DURATION in days | COMMENTS | STATUS
1 | PROJECT CONCEPTION AND INITIATION | Complete |  | 2024-01-02 | 2024-02-09 | 39 |  | Not Started
1.1 | – Project Charter | Complete |  | 2024-01-02 | 2024-01-11 | 10 |  | In Progress
1.1.1 | –– Project Charter Revisions | Complete |  | 2024-01-07 | 2024-01-11 | 5 |  | Complete
1.2 | – Research | Complete |  | 2024-01-10 | 2024-02-23 | 45 |  | On Hold
1.3 | – Projections | Complete |  | 2024-01-10 | 2024-01-20 | 11
1.4 | – Stakeholders | Complete |  | 2024-01-16 | 2024-01-29 | 14
1.5 | – Guidelines | In Progress |  | 2024-01-19 | 2024-02-01 | 14
1.6 | – Project Initiation | In Progress |  | 2024-01-22 | 2024-02-09 | 19
2 | PROJECT DEFINITION AND PLANNING | In Progress |  | 2024-01-28 | 2024-02-14 | 18
2.1 | – Scope & Goal Setting | On Hold |  | 2024-01-28 | 2024-02-06 | 10
2.2 | – Budget | In Progress |  | 2024-01-31 | 2024-02-02 | 3
2.3 | – Communication Plan | In Progress |  | 2024-02-04 | 2024-02-12 | 9
2.4 | – Risk Management | Complete |  | 2024-02-06 | 2024-02-14 | 9
3 | PROJECT LAUNCH & EXECUTION | Complete |  | 2024-02-18 | 2024-03-26 | 38
3.1 | – Status & Tracking | In Progress |  | 2024-02-18 | 2024-02-20 | 3
3.2 | – KPIs | In Progress |  | 2024-02-18 | 2024-02-23 | 6
3.2.1 | –– Monitoring | In Progress |  | 2024-02-18 | 2024-02-26 | 9
3.2.2 | –– Forecasts | Not Started |  | 2024-02-21 | 2024-02-23 | 3
3.3 | – Project Updates | Not Started |  | 2024-02-22 | 2024-02-23 | 2
3.3.1 | –– Chart Updates | In Progress |  | 2024-02-25 | 2024-03-26 | 31
4 | PROJECT PERFORMANCE / MONITORING | In Progress |  | 2024-02-25 | 2024-03-26 | 31
4.1 | – Project Objectives | In Progress |  | 2024-02-25 | 2024-02-28 | 4
4.2 | – Quality Deliverables | On Hold |  | 2024-02-26 | 2024-03-03 | 7
4.3 | – Effort & Cost Tracking | Not Started |  | 2024-02-25 | 2024-03-06 | 11
4.4 | – Project Performance | Not Started |  | 2024-03-03 | 2024-03-26 | 24

## BLANK - Master Project Schedule
MASTER PROJECT SCHEDULE
| PROJECT TITLE |  | START DATE
| Sistema de Monitoreo de Salud |  | 2025-02-20 |  |  | PROJECT DURATION
| PROJECT MANAGER |  |  |  |  | in days
| Tenoch Moreno |  | 2025-05-09 |  |  | 79
WBS NO. | TASK NAME | STATUS | ASSIGNED TO | START DATE | END DATE | DURATION in days | COMMENTS | STATUS
1 | PROYECT REQUERIMENT |  |  |  |  | 1 |  | Not Started
1.1 | Lectura de dicumentacion | Complete | Christian Ojeda, Tenoch Moreno | 2025-02-19 | 2025-02-20 | 2 |  | In Progress
1.1.1 | Analisis de requerimientos | Complete | Alejandro Juncal | 2025-02-23 | 2025-02-26 | 4 |  | Complete
1.4 | Aclaracion de dudas | In Progress |  |  |  | 1
1.5 | Analisis de Objetivos | In Progress | Tenoch Moreno | 2025-02-26 |  | -45713
1.6 | Creacion de repositorio en github | In Progress |  |  |  | 1
2 | PROYECT DESIGN |  |  |  |  | 1
2.1 | Definicion de Tecnologias | In Progress | Christian Ojeda |  |  | 1
2.2 | Definicion de la estructura de proyecto | In Progress | Alejandro Juncal, Christian Ojeda, Tenoch Moreno |  |  | 1
2.3 | Definicion de Etapas |  |  |  |  | 1
2.4 | Diseño conceptual de la base de Datos
2.5 | Solucion para creacion del software |  |  |  |  | 1
3 | PROYECT DEVELOPMENT |  |  |  |  | 1
| Levantar un servidor http | Not Started | Alejandro y Christian Ojeda |  |  | 1
| Creacion de Base de Datos | Not Started | Tenoch Moreno
| Cimientos del back-end | Not Started | Alejandro Juncal |  |  | 1
| Creacion de la interfaz basica del usuario | Not Started | Christian Ojeda |  |  | 1
| Implementacion de seguridad en Back-end | Not Started | Alejandro Juncal |  |  | 1
| Creacion de funciones en Back-end | Not Started | Alejandro Juncal |  |  | 1
| Sincronizacion de Front y Back-end | Not Started | Christian Ojeda
| Sincronizacion de Base de Datos y Back-end | Not Started | Tenoch Moreno |  |  | 1
4 | TESTING |  |  |  |  | 1
4.1 | – Project Objectives |  |  |  |  | 1
4.2 | – Quality Deliverables |  |  |  |  | 1
4.3 | – Effort & Cost Tracking |  |  |  |  | 1
4.4 | – Project Performance |  |  |  |  | 1
5 | MAINTANANCE |  |  |  |  | 1
4.1 | – Project Objectives |  |  |  |  | 1
4.2 | – Quality Deliverables |  |  |  |  | 1
4.3 | – Effort & Cost Tracking |  |  |  |  | 1
4.4 | – Project Performance |  |  |  |  | 1
Double-click Horizontal (Value) Axis to format Bound Minimum and Bound Maximum settings under Axis Options.* Delete any unpopulated rows in your table.*

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.